## Slide 1: Jaunt Rural Transit Needs Assessment
Project Overview

## Slide 2: Research Team
Jeremy Mattson – Associate Professor, Small Urban and Rural Center on Mobility (SURCOM), North Dakota State University (NDSU)
Jill Hough – Director, SURCOM, NDSU

## Slide 3: Study Objectives
Construct demographic profile of the Jaunt service area
Develop a mobility needs index
Describe existing levels of transit service across the study area
Identify base levels of desired transit service and gaps in existing service
Develop recommendations for meeting mobility needs

## Slide 4: Scope of Study
Counties of Albermarle, Buckingham, Fluvanna, Goochland, Greene, Louisa, Nelson
City of Charlottesville
Local public transportation, human service transportation
Jaunt wants to quantify how much transit services are needed in each of its partner jurisdictions.

## Slide 5: Work Plan
Task 1. Stakeholder Involvement
Task 2. Develop a demographic profile and mobility needs index of the study area
Task 3. Describe and evaluate existing levels of passenger transportation services with study area
Task 4. Establish mobility goals and identify service gaps, transit needs, and funding requirements
Task 5. Identify options and recommendations
Task 6. Develop final deliverables

## Slide 6: Task 1. Stakeholder Involvement
Project kickoff meeting
Online surveys/interviews
Meeting with preliminary results
Meeting after draft report completed

## Slide 7: Task 2. Develop a demographic profile and mobility needs index of the study area
Population density
Demographics
  Older adults (age 65+)
  People with a disability
  Low income
  Households with no vehicle
  Youth (age 10-17)
Mobility Needs Index
Projected population growth

## Slide 8: Population Density

## Slide 9: Older Adult Population

## Slide 10: Youth Population

## Slide 11: Population with a Disability

## Slide 12: Low-Income Population

## Slide 13: Households with No Vehicles

## Slide 14: Mobility Needs Index
Based on Percentage of Population
Based on Population Density

## Slide 15: Task 3. Describe and evaluate existing levels of passenger transportation services within the service area
Service description: Types of service, Span of service (days, hours, frequency)
Operating data
  Ridership
  Vehicle revenue miles
  Vehicle revenue hours
  Characteristics of riders
Financial data
Vehicles/facilities
Performance measures

## Slide 16: Task 3. (continued)
Calculate per capita measures
  Trips per capita
  Vehicle revenue miles per capita
  Vehicle revenue hours per capita
Calculate measures per transportation disadvantaged population: trips per population aged 65 or older, trips per low-income population, etc.
Calculate measures at the county or census tract level where possible

## Slide 17: Example: Mapping Rural Service Levels Across North Dakota

## Slide 18: Task 4. Establish mobility goals and identify service gaps, transit needs, and funding requirements
Identify goals or targets
  Peer analysis
  Stakeholder input
Compare performance/service levels to goals
  By county and by census tract
Identify service gaps
Calculate increased service needed to meet goals
  Consider different scenarios
  Account for projected population growth
  Calculate funding requirements

## Slide 19: Task 5. Identify options and recommendations
Identify options for service improvements
Provide recommendations for where to prioritize service improvements
Seek feedback from stakeholders

## Slide 20: Task 6. Prepare final report
Detailed research report
Summary report

## Slide 21: Timeline
Task 2: Mostly completed
Task 3: Sept – Nov
Stakeholder meeting: Tentatively early December
Task 4: Nov – Jan
Task 5: Feb
Stakeholder meeting: Feb-March
Draft report completed around April
Final report completed by end of June

## Slide 22: Discussion
Contact info:
Jeremy Mattson – jeremy.w.mattson@ndsu.edu
Jill Hough – jill.hough@ndsu.edu